## Matrix
Azure Services Project Estimation Model |  | Evaluation | Discovery | Validation | Deployment & Integration | Restructuring Apps | Migration (Servers) | Migration (Apps) | Testing Effort | Totals (hrs) w/o Contigency | Totals (hrs) w/ Contigency
Inputs
Number of Applications | 3
Number of Servers | 5
Effort per Migration (hrs) | 8
Apps/ Server Evaluate Effort (hrs) | 5
Core
Applications effort to determine Migration Strategy |  | 15 | [7 empty] | 15
Apps/ Servers Deployment Set-up |  |  |  |  | 40 |  |  |  |  | 40
Restructing Apps to align with Cloud needs | [5 empty] | 15 |  |  |  | 15
Testing Efforts for restructured applications | [8 empty] | 15 | 15
Testing Efforts for migration Servers (connectivity, data sync) | [8 empty] | 25 | 25
Validate provisioned destination servers meet Client prerequisites |  |  |  | 0 | [5 empty] | 0
Estimate average per migration effort based on discovery | [6 empty] | 40 | 24 |  | 64
Contingency
Anomalies encountered in discovery of the application |  | 15 | [8 empty] | 15
Application product issues |  |  | 0 | [7 empty] | 0
Failure to engage App Owners / limited application knowledge |  |  |  | 15 | [6 empty] | 15
Failure to meet prerequisites that require change control | [6 empty] | 8 |  |  |  | 8
Failure to accurately fit migration change windows | [6 empty] | 8 |  |  |  | 8
General application troubleshooting / remediation | [6 empty] | 8 |  |  |  | 8
Lack of App Owner availability to exercise / test the application | [6 empty] | 8 |  |  |  | 8
Totals |  | 30 | 0 | 15 | 40 | 15 | 72 | 24 | 40 | 174 | 236